## Milestone_Log
Milestone_ID | Milestone_Name | Key_Decision | Phase | Decision_Date | Status | Verification_Status | Next_Action | Approval_Signal | Remaining_Risk | Verification_Evidence | Owner | Source_of_Truth | Files_Affected | Notes
MS-001 | Architecture Source Separation | Separate live market price fetching in base app from scheduled macro data ingestion; macro_pack_latest is source of truth for macro outputs. | Architecture | 24/6/2026 | LOCKED | PARTIAL | Run base-app data-source governance patch and validation scan. | Prior locked decision | Old app defaults can still leak into production display/scoring if not quarantined. | Base app is pack-aware but not fully pack-governed; legacy PMI fallback paths still need cleanup. | Wisni Tan / Copilot | DATA_SOURCE_POLICY.csv / macro_pack_latest outputs | sg_tactical_wealth_allocator.py; macro_pack_latest/macro_data.csv; macro_pack_latest/macro_history_12m.csv; macro_pack_latest/rates_history_252d.csv | Core principle: base app consumes macro pack outputs, not recreate macro defaults.
MS-002 | Rates Live API Policy | Decisions 1–4 rates use live APIs only; avoid unreliable monthly macro pack rates source where live route is available. | Data Source Policy | 24/6/2026 | LOCKED | PENDING | Fix KLSE/BNM day-first date parsing and verify latest OPR date. | Prior locked decision | Date parser can misread BNM DD/MM/YYYY as MM/DD/YYYY if not fixed. | Rates history workflow exists; KLSE date parser issue remains pending. | Wisni Tan / Copilot | macro_pack_latest/rates_history_252d.csv; live rates adapters | update_rates_history_252d.py; update_rates_history_252d.yml; macro_pack_latest/rates_history_252d.csv | BNM OPR date should be interpreted day-first.
MS-003 | SG SORA Runtime Source Policy | Remove legacy MAS secure/eservices datastore/API endpoints from active SG SORA fetch path; use live redistributor-only route due to runtime failures. | Data Source Policy | 25/6/2026 | LOCKED | LOCKED_NOT_FULLY_RETESTED | Keep source note in tooltip/diagnostics and avoid reintroducing MAS legacy endpoints. | Prior locked decision | Redistributor availability should be monitored in diagnostics. | Policy locked after runtime/gaierror issues. | Wisni Tan / Copilot | DATA_SOURCE_POLICY.csv; SG SORA adapter notes | g20_macro_fetcher.py; SG SORA adapter logic; macro_pack_latest/macro_data.csv | No fallback to removed MAS endpoints unless separately revalidated.
MS-004 | APAC Macro Live API Policy | MY unemployment, JP unemployment and JP inflation use live APIs due to unreliable monthly macro pack data. | Data Source Policy | 24/6/2026 | LOCKED | PENDING | Validate latest values and source_type in macro_data.csv after each workflow run. | Prior locked decision | API endpoint changes or stale annual fallback can mislead timing signals. | Live API route selected by policy; output validation still needed market-by-market. | Wisni Tan / Copilot | macro_pack_latest/macro_data.csv | g20_macro_fetcher.py; macro_pack_latest/macro_data.csv; diagnostics.csv | Annual fallback should not be presented as monthly market-timing signal.
MS-005 | Base App UI Governance | Hide Owner Mode during user testing; move Macro Data Manager and Macro Adapter Diagnostics into Audit, Methodology & Export as collapsed admin/tooling sections; keep Refresh Market Data in sidebar. | UI / UX | 26/6/2026 | LOCKED | PARTIAL | Keep UI admin/tooling features collapsed in Audit. | Prior locked decision | Future UI patches may reintroduce sidebar clutter. | Base app review showed Owner Mode hidden and admin/source tooling under audit section. | Wisni Tan / Copilot | GLOBAL20ENGINE_MILESTONE_LOG.csv; base app UI sections | sg_tactical_wealth_allocator.py | User-testing mode should remain clean.
MS-006 | Dashboard Layout Governance | Live Market & Trend Monitor collapsed by default; remove duplicated top Market Conditions KPI cards; keep Yahoo-style index chart; keep 12M Macro Snapshot macro-only; keep valuation/drawdown/risk diagnostics collapsed by default. | UI / UX | 26/6/2026 | LOCKED | PARTIAL | Verify layout after next full base-app build. | Prior locked decision | Dashboard may become too long if collapsed defaults are changed. | Base app contains Live Market & Trend Monitor and 12M Macro Snapshot sections; further UI verification still required after final patch. | Wisni Tan / Copilot | GLOBAL20ENGINE_MILESTONE_LOG.csv; base app UI sections | sg_tactical_wealth_allocator.py | Priority is decision clarity and compact review.
MS-007 | Macro Risk Score v2 Model | Upgrade from old 3-indicator model to weighted multi-factor Macro Risk Score v2 using applicable inflation, unemployment/claims, PMI, rates, yield curve and VIX; exclude N/A and re-normalise weights; source quality belongs in tooltip, not direct penalty. | Model / Scoring | 26/6/2026 | LOCKED_PATCH_PENDING | PENDING | Patch Macro Risk Score to fail closed or show partial instead of silent default fallback. | Prior locked decision | Legacy PMI/session defaults may still influence risk score if macro pack data missing. | Base app has v2-style components but PMI fallback leakage remains possible. | Wisni Tan / Copilot | DATA_SOURCE_POLICY.csv; base app risk score logic | sg_tactical_wealth_allocator.py | Important model governance item.
MS-008 | 12M Macro Snapshot Mini-Chart KIV | Stop further mini-chart/UI patching for 12M Macro & Market Trend Snapshot unless quick data-only fix exists; remaining one-point charts are data-coverage gaps, not UI blockers. | UI / Data Coverage | 27/6/2026 | KIV | KIV | Do not prioritise UI patch; improve data coverage through workflow outputs. | Prior KIV decision | Some charts may remain one-point or unavailable until history improves. | User explicitly decided not to spend further time unless quick data-only fix exists. | Wisni Tan / Copilot | GLOBAL20ENGINE_MILESTONE_LOG.csv | sg_tactical_wealth_allocator.py; macro_pack_latest/macro_history_12m.csv; macro_pack_latest/rates_history_252d.csv | This should be surfaced if future requests revisit mini-charts.
MS-009 | Executive Market Summary Design | Executive summary should mirror market main page and provide cross-market drawdown-led scorecard with tooltip-guided Action and Suggested Deploy, not a buy call. | UI / Executive Centre | 28/6/2026 | DISCUSSED_MOCKUP_CREATED | DESIGN_REVIEW_PENDING | Implement only after data-source governance patch is complete. | Mockup requested | Design not yet implemented in base app. | PNG mockup generated for review. | Wisni Tan / Copilot | Executive summary mockup PNG; future app implementation | sg_tactical_wealth_allocator.py; mockup PNG | Keep concise and decision-focused.
MS-010 | PMI Source Governance | PMI production values must come from macro_data.csv; hardcoded/default/seed PMI must not drive production cards, Macro Risk Score or Growth regime; manual PMI only Audit/Admin, mainly China/A-Share exception. | Data Source Governance | 29/6/2026 | LOCKED_PATCH_PENDING | PENDING | Patch base app and regime builder to read macro_data.csv first and block silent fallback. | let proceed / prior approval signals | Derived regime output and base app legacy pathways can still point to old defaults. | macro_data.csv has PMI rows but global_macro_regime_latest showed Growth FALLBACK from App PMI defaults composite. | Wisni Tan / Copilot | macro_pack_latest/macro_data.csv | sg_tactical_wealth_allocator.py; macro_pack_latest/macro_data.csv; macro_pack_latest/macro_history_12m.csv; global_macro_regime_latest.csv/regime builder | This is the current priority bug class.
MS-011 | Base App Data-Source Governance Audit | Base app is pack-aware but not fully pack-governed; quarantine PMI_PROXY_MAP, LATEST_PMI_ACTUALS, DEFAULT_PMI_HISTORY, PMI_DEFAULTS and PMI_SOURCE_CHAINS from production scoring/display. | Base App Governance | 29/6/2026 | LOCKED_PATCH_PENDING | PENDING | Perform consolidated source-routing patch, not piecemeal PMI-only patch. | let proceed / governance approval | Same mismatch can return if old fallback paths remain. | Base app review found legacy PMI structures and fallback leakage risk. | Wisni Tan / Copilot | GLOBAL20ENGINE_MILESTONE_LOG.csv; DATA_SOURCE_POLICY.csv | sg_tactical_wealth_allocator.py | No production dashboard value should come from hardcoded macro defaults when macro_data.csv has valid row.
MS-012 | Milestone Governance Process | Use milestone log as source-of-truth; Copilot provides short checklist for future changes; update milestone log only after explicit approval signal. | Governance | 29/6/2026 | LOCKED | PATCHED | Commit CSV log into docs folder and use it going forward. | let proceed | Old milestones were initially missing from Markdown log; this CSV adds historical milestones. | Initial docs folder created and committed; CSV version now generated to replace/augment Markdown log. | Wisni Tan / Copilot | docs/GLOBAL20ENGINE_MILESTONE_LOG.csv | docs/GLOBAL20ENGINE_MILESTONE_LOG.csv; docs/DATA_SOURCE_POLICY.csv; docs/CHANGE_VERIFICATION_CHECKLIST.csv | Accepted approval signals include please proceed, proceed, APPROVE, approve, lock this, good to go, yes proceed, let proceed.

## README
CSV vs Excel formatting
CSV stores data only. It cannot preserve fixed column widths or wrap formatting in GitHub preview.
Use this XLSX version for fixed-width, wrapped review. Keep CSV as the GitHub/source-control source of truth.
Recommended workflow
1. Maintain GLOBAL20ENGINE_MILESTONE_LOG.csv as source-of-truth.
2. Use GLOBAL20ENGINE_MILESTONE_LOG_wrapped.xlsx for easier reading/review.
3. If editing in Excel, export back to CSV before committing.